{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["2025年第四批"],"not_rendered":{"defined_names":1},"read":"whole","date_system":"1900"}

{"sheet":"2025年第四批","index":0,"n_rows":184,"n_cols":21,"rows_kept":184,"merged":[[0,0,0,1],[1,0,1,19]]}
["附表"]
["渝水区2025年度巩固拓展脱贫攻坚成果同乡村振兴有效衔接项目（第四批）安排表"]
["序号","项目类别","项目名称","实施单位乡镇","实施村","项目责任人","建设性质","实施地点村","实施地点村小组","建设任务","资金规模（万元）","筹资方式或资金来源","绩效目标","联农带农富农机制","受益脱贫户和监测对象户数","受益脱贫人口和监测对象人数","实施开始结束期限","补助标准","行业主管部门","村类型","备注"]
[1,"乡村建设行动","路灯","鹄山镇","鹄山村","黄平","新建","鹄山村","鹄山组","太阳能路灯77盏",10,"衔接资金","产出指标：太阳能路灯≥77盏，效益指标：受益脱贫人口和监测对象≥84人、增加劳动力总收入≥1000元；满意度指标：受益对象满意度≥95%","项目建设时吸纳脱贫人口和监测对象参工参运≥2人",38,84,"2025年8-12月","10万元/处","区农业农村和粮食局","区级重点帮扶村"]
[2,"乡村建设行动","路灯","鹄山镇","鹄山村","黄平","新建","鹄山村","集镇","太阳能路灯90盏",13,"衔接资金","产出指标：太阳能路灯≥90盏，效益指标：受益脱贫人口和监测对象≥84人、增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥95%","项目建设时吸纳脱贫人口和监测对象参工参运≥2人",38,84,"2025年8-12月","13万元/处","区农业农村和粮食局","区级重点帮扶村"]
[3,"乡村建设行动","果业加工产业基础设施","鹄山镇","上塘村","简芝良","新建","上塘村","上塘组","挡土墙100m\n沟120m\n砼路面230㎡",11,"衔接资金","产出指标：挡土墙≥100m、沟≥120m、砼路面≥230㎡；效益指标：受益脱贫人口和监测对象≥30人，增加劳动力总收入≥1100元；满意度指标：受益对象满意度≥94%","支持产业发展，项目建设时吸纳脱贫人口和监测对象参工参运≥1人",15,30,"2025年8-12月","11万元/处","区农业农村和粮食局","区级重点帮扶村"]
[4,"乡村建设行动","道路硬化","鹄山镇","上塘村","简芝良","新建","上塘村","南港组","道路硬化430m",13,"衔接资金","产出指标：道路硬化≥430m，效益指标：受益脱贫人口和监测对象≥76人、增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥95%","方便村民出行，项目建设时吸纳脱贫人口和监测对象参工参运≥1人",39,76,"2025年8-12月","13万元/处","区农业农村和粮食局","区级重点帮扶村"]
[5,"乡村建设行动","渠道","鹄山镇","晓堆村","肖海星","新建","晓堆村","晓堆组","渠道410m",14,"衔接资金","产出指标：渠道≥410m；效益指标：受益脱贫人口和监测对象≥21人，增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥95%","完善本村农田水利灌溉系统，项目建设时吸纳脱贫人口和监测对象参工参运≥2人",21,41,"2025年8-12月","14万元/处","区农业农村和粮食局","普通村"]
[6,"乡村建设行动","路灯","鹄山镇","递步村","胡小强","新建","递步村","上塘组","太阳能路灯85盏",11,"衔接资金","产出指标：太阳能路灯≥85盏；效益指标：受益脱贫人口和监测对象≥61人、增加劳动力总收入≥1100元；满意度指标：受益对象满意度≥95%","方便村民夜间出行，项目建设时吸纳脱贫人口和监测对象参工参运≥2人",32,61,"2025年8-12月","11万元/处","区农业农村和粮食局","普通村"]
[7,"乡村建设行动","渠道","鹄山镇","桐村村","简海平","新建","桐村村","桐村组","渠道220m",6,"衔接资金","产出指标：渠道≥220m；效益指标：受益脱贫人口和监测对象≥37人，增加劳动力总收入≥600元；满意度指标：受益对象满意度≥95%","完善本村农田水利灌溉系统，项目建设时吸纳脱贫人口和监测对象参工参运≥1人",17,37,"2025年8-12月","6万元/处","区农业农村和粮食局","普通村"]
[8,"乡村建设行动","路灯","鹄山镇","窝里村","习小龙","新建","窝里村","脑老组","太阳能路灯78盏",10,"衔接资金","产出指标：太阳能路灯≥78盏；效益指标：受益脱贫人口≥69人，增加劳动力总收入≥1000元；满意度指标：受益对象满意度≥95%","方便夜间出行，项目建设时吸纳脱贫人口参工参运≥2人",34,69,"2025年8-12月","10万元/处","区农业农村和粮食局","区级重点帮扶村"]
[9,"乡村建设行动","路面硬化","界水乡","横塘村","钟志敏","新建","横塘村","李家组","砼路330m",10.5,"衔接资金","产出指标：砼路≥330m；效益指标：受益人口≥8人，其中受益脱贫人口和监测对象≥8人,增加劳动力收入≥1050元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人,",4,7,"2025年8-12月","10.5万元/处","区农业农村和粮食局","普通村"]
[10,"乡村建设行动","路灯","界水乡","黄溪村","邹国宇","新建","黄溪村","夫山组","太阳能路灯93盏",12,"衔接资金","产出指标：太阳能路灯≥93盏；效益指标：受益脱贫人口和监测对象≥60人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥95%","方便村民夜间出行，吸纳脱贫人口和监测对象参工参运≥2人，助力脱贫户增收",4,6,"2025年8-12月","12万元/处","区农业农村和粮食局","区级重点帮扶村"]
[11,"乡村建设行动","排水沟","良山镇","鹊桥村","周腾保","新建","鹊桥村","妙山组","沟400m\n砼路70m",12,"衔接资金","产出指标：沟≥400m、砼路≥70m；效益指标：受益脱贫人口和监测对象≥3人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",2,3,"2025年8-12月","12万元/处","区农业农村和粮食局","普通村"]
[12,"乡村建设行动","村庄整治","良山镇","舍山村","袁庆生","新建","舍山村","黄屯组","砼路面600㎡\n沟300m\n太阳能路灯40盏",14,"衔接资金","产出指标：砼路面≥600㎡、沟≥300m、太阳能路灯≥40盏；效益指标：受益脱贫人口和监测对象≥7人，增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",4,7,"2025年8-12月","14万元/处","区农业农村和粮食局","区级重点帮扶村"]
[13,"乡村建设行动","村庄整治","罗坊镇","陂下村","宋小勇","新建","陂下村","长湖组","砼路176m\n地面硬化470㎡\n太阳能路灯15盏",13,"衔接资金","产出指标：砼路≥176m、地面硬化≥470㎡、太阳能路灯≥15盏；效益指标：受益人口≥267人，其中受益脱贫人口和监测对象≥3人，增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥1人",1,3,"2025年8-12月","13万元/处","区农业农村和粮食局","区级重点帮扶村"]
[14,"乡村建设行动","路灯","罗坊镇","川里村","欧阳四根","新建","川里村","川里组","太阳能路灯77盏",10,"衔接资金","产出指标：太阳能路灯≥77盏；效益指标：受益人口≥1100人，其中脱贫人口和监测对象≥18人，增加劳动力总收入≥1000元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",10,18,"2025年8-12月","10万元/处","区农业农村和粮食局","普通村"]
[15,"乡村建设行动","路灯","罗坊镇","东边村","宋卫保","新建","东边村","东边组","太阳能路灯38盏",5,"衔接资金","产出指标：太阳能路灯≥38盏；效益指标：受益人口≥307人，其中脱贫人口和监测对象≥6人，增加劳动力总收入≥500元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥1人",2,6,"2025年8-12月","5万元/处","区农业农村和粮食局","市级重点帮扶村"]
[16,"乡村建设行动","路面硬化","罗坊镇","高磡村","钟明峰","新建","高磡村","新屋组","砼路360m",13,"衔接资金","产出指标：砼路≥360m；效益指标：受益人口≥576人，其中脱贫人口和监测对象≥11人，增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",7,11,"2025年8-12月","13万元/处","区农业农村和粮食局","普通村"]
[17,"乡村建设行动","路面硬化","罗坊镇","胡家村","胡磊","新建","胡家村","蔡家组","砼路380m",13,"衔接资金","产出指标：砼路380m；效益指标：受益人口≥271人，受益脱贫人口和监测对象≥6人，增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",3,6,"2025年8-12月","13万元/处","区农业农村和粮食局","普通村"]
[18,"乡村建设行动","村庄整治","罗坊镇","胡家村","胡磊","新建","胡家村","胡家组","沟200m\n太阳能路灯30盏\n挡土墙240m",13,"衔接资金","产出指标：挡土墙≥240m、沟≥200m、太阳能路灯≥30盏；效益指标：受益人口≥310人，受益脱贫人口和监测对象≥10人，增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥95%.","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",5,10,"2025年8-12月","13万元/处","区农业农村和粮食局","普通村"]
[19,"乡村建设行动","路面硬化","罗坊镇","开元村","周小武","新建","开元村","增家组","砼路270m",12,"衔接资金","产出指标：砼路≥270m；效益指标：受益人口≥211人，其中脱贫人口和监测对象≥11人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",5,11,"2025年8-12月","12万元/处","区农业农村和粮食局","区级重点帮扶村"]
[20,"乡村建设行动","村庄整治","罗坊镇","刘家村","刘菊根","新建","刘家村","方田组","地面硬化1100㎡\n沟56m",12,"衔接资金","产出指标：地面硬化≥1100㎡、沟≥56m；效益指标：受益人口≥269人，其中受益脱贫人口和监测对象≥8人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",3,8,"2025年8-12月","12万元/处","区农业农村和粮食局","区级重点帮扶村"]
[21,"乡村建设行动","村庄整治","罗坊镇","梦塘村","刘利辉","新建","梦塘村","孙溪组","挡土墙40m\n沟57m\n砼路面600㎡\n太阳能路灯48盏",14.5,"衔接资金","产出指标：砼路面≥600㎡、挡土墙≥40m、沟≥57m、太阳能路灯≥48盏；效益指标：受益人口≥142人，其中脱贫人口和监测对象≥6人，增加劳动力总收入≥1450元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",3,6,"2025年8-12月","14.5万元/处","区农业农村和粮食局","普通村"]
[22,"乡村建设行动","村庄整治","罗坊镇","梦塘村","刘利辉","新建","梦塘村","易家组","砼路面259㎡\n砖沟88m\n太阳能路灯68盏",13,"衔接资金","产出指标：砼路面≥259㎡、砖沟≥88m、太阳能路灯≥68盏；效益指标：受益人口≥142人，其中脱贫人口和监测对象≥16人，增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",6,16,"2025年8-12月","13万元/处","区农业农村和粮食局","普通村"]
[23,"乡村建设行动","地面硬化","罗坊镇","彭家村","彭小平","新建","彭家村","邓家组","地面硬化1500㎡",9,"衔接资金","产出指标：地面硬化≥1500㎡；效益指标：受益人口≥414人，其中脱贫人口和监测对象≥10人，增加劳动力总收入≥900元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",4,10,"2025年8-12月","9万元/处","区农业农村和粮食局","省市红色名村"]
[24,"乡村建设行动","路面硬化","罗坊镇","平塘村","廖小军","新建","平塘村","社山组","砼路396m",15,"衔接资金","产出指标：砼路≥396m；效益指标：受益人口≥308人，其中脱贫人口和监测对象≥3人，增加劳动力总收入≥1500元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",1,3,"2025年8-12月","15万元/处","区农业农村和粮食局","普通村"]
[25,"乡村建设行动","村庄整治","罗坊镇","沙滩村","李俊","新建","沙滩村","永子洲组","挡土墙80m\n沟55m\n砼路190m",12,"衔接资金","产出指标：砼路≥190m、挡土墙≥80m、沟≥55m；效益指标：受益人口≥74人，其中脱贫人口和监测对象≥3人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",1,3,"2025年8-12月","12万元/处","区农业农村和粮食局","普通村"]
[26,"乡村建设行动","地面硬化","罗坊镇","嵩山村","廖火金","新建","嵩山村","大路组","地面硬化1200㎡",12,"衔接资金","产出指标：地面硬化≥1200㎡m；效益指标：受益人口≥860人，其中脱贫人口和监测对象≥1人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",10,19,"2025年8-12月","12万元/处","区农业农村和粮食局","“十四五”省级重点帮扶村"]
[27,"乡村建设行动","农产品加工产业路","罗坊镇","山田村","刘学杰","新建","山田村","中堎组","砼路面1150㎡",12,"衔接资金","产出指标：砼面≥1150㎡；效益指标：受益人口≥268人，其中脱贫人口和监测对象≥13人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",5,13,"2025年8-12月","12万元/处","区农业农村和粮食局","普通村"]
[28,"乡村建设行动","村庄整治","罗坊镇","水东村","刘春云","新建","水东村","老楼下组","透水混凝土地面1050㎡\n砼地面1160㎡\n沟102m",19,"衔接资金","产出指标：透水混凝土地面≥1050㎡、砼地面≥1160㎡、沟≥102m；效益指标：受益人口≥722人，其中脱贫人口和监测对象≥19人，增加劳动力总收入≥1900元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",6,19,"2025年8-12月","19万元/处","区农业农村和粮食局","普通村"]
[29,"乡村建设行动","道路硬化","罗坊镇","王年村","廖晓军","新建","王年村","园田坑组","砼路230m",12,"衔接资金","产出指标：砼路≥230m；效益指标：受益脱贫人口和监测对象≥7人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",4,7,"2025年8-12月","12万元/处","区农业农村和粮食局","普通村"]
[30,"乡村建设行动","道路硬化","罗坊镇","新和村","毛海兵","新建","新和村","清坑组","砼路380m",14,"衔接资金","产出指标：砼路≥380m；效益指标：受益人口≥76人，其中脱贫人口和监测对象≥11人，增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",7,11,"2025年8-12月","14万元/处","区农业农村和粮食局","区级重点帮扶村"]
[31,"乡村建设行动","路面硬化","罗坊镇","院前村","郭云牯","新建","院前村","周家坑组","砼路330m",12,"衔接资金","产出指标：砼路≥330m；效益指标：受益人口≥568人，其中脱贫人口和监测对象≥9人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",4,9,"2025年8-12月","12万元/处","区农业农村和粮食局","省市红色名村"]
[32,"乡村建设行动","道路硬化","罗坊镇","章塘村","傅春平","新建","章塘村","下坑组","砼路390m",14,"衔接资金","产出指标：砼路≥390m；效益指标：受益人口≥144人，其中受益脱贫人口和监测对象≥6人，增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",2,6,"2025年8-12月","14万元/处","区农业农村和粮食局","区级重点帮扶村"]
[33,"乡村建设行动","村庄整治","罗坊镇","官塘村","邓九芽","新建","官塘村","芙蓉组","砼路面430㎡\n地面硬化380㎡\n砖砌挡土墙28m\n太阳能路灯15盏",10,"衔接资金","产出指标：砼路面≥430㎡、地面硬化≥380㎡、挡土墙≥28m、太阳能路灯≥15盏；效益指标：受益人口≥268人，其中受益脱贫人口和监测对象≥11人，增加劳动力总收入≥1000元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人,增加收入≥500元/人",4,11,"2024年8-11月","10万元/处","区农业农村和粮食局","普通村"]
[34,"乡村建设行动","排水沟","南安乡","丰洲村","赵卫豪","新建","丰洲村","新村组","沟长125m净宽0.7m净高0.8m墙厚0.15m",6,"衔接资金","产出指标：沟≥125m；效益指标：受益脱贫户和监测对象≥10人，增加劳动力总收入≥600元，满意度指标：受益对象满意度≥93%","项目建设吸纳脱贫人口和监测对象参工参运≥2人，增加收入",4,10,"2025年8-12月","6万元/处","区农业农村和粮食局","区级重点帮扶村"]
[35,"乡村建设行动","排水沟","南安乡","丰洲村","赵卫豪","新建","丰洲村","晏家组","沟长155m净宽0.5m净高0.6m墙厚0.24m",5,"衔接资金","产出指标：沟≥155m；效益指标：受益脱贫户和监测对象≥1人，增加劳动力总收入≥500元；满意度指标：受益对象满意度≥93%","项目建设吸纳脱贫人口和监测对象参工参运≥1人，增加收入",1,1,"2025年8-12月","5万元/处","区农业农村和粮食局","区级重点帮扶村"]
[36,"乡村建设行动","路灯","南安乡","高峰村","章小勇","新建","高峰村","余家组","太阳能路灯93盏",12,"衔接资金","产出指标：太阳能路灯≥93盏；效益指标:受益脱贫人口和监测对象≥6人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥93%","方便村民夜间出行条件，吸纳脱贫人口和监测对象参工参运≥2人，增加收入",6,6,"2025年8-12月","12万元/处","区农业农村和粮食局","区级重点帮扶村"]
[37,"乡村建设行动","路灯","南安乡","显华村","易细明","新建","显华村","洋溪组","太阳能路灯47盏",6,"衔接资金","产出指标：太阳能路灯≥47盏；效益指标：受益脱贫人口和监测对象≥4人，增加劳动力总收入≥600元；满意度指标：受益对象满意度≥93%","方便村民夜间出行条件，吸纳脱贫人口和监测对象参工参运≥2人，增加收入",3,4,"2025年8-12月","6万元/处","区农业农村和粮食局","普通村"]
[38,"乡村建设行动","路灯","南安乡","荆兰村","易艳荣","新建","荆兰村","潢溪组","太阳能路灯62盏",8,"衔接资金","产出指标：太阳能路灯≥62盏；效益指标：受益脱贫户和监测对象≥3人；增加劳动力总收入≥800元，满意度指标：受益对象满意度≥93%","方便村民夜间出行条件，吸纳脱贫人口和监测对象参工参运≥1人，增加收入",2,3,"2025年8-12月","8万元/处","区农业农村和粮食局","区级重点帮扶村"]
[39,"乡村建设行动","排水沟","南安乡","荆兰村","易艳荣","新建","荆兰村","荆兰组","沟长280m宽0.8m高0.8m厚0.16m",13,"衔接资金","产出指标：沟≥280m；效益指标：受益脱贫户和监测对象≥16人；增加劳动力总收入≥1300元，满意度指标：受益对象满意度≥95%","项目建设时吸纳脱贫人口参工参运≥2人，助力乡村振兴",7,16,"2025年8-12月","13万元/处","区农业农村和粮食局","区级重点帮扶村"]
[40,"乡村建设行动","蛋鸭养殖基地产业路","人和乡","布里村","李火珠","新建","布里村","枫树下组","产业路1600㎡",15,"衔接资金","产出指标：产业路≥1600㎡；效益指标：受益脱贫人口和监测对象≥6人，增加劳动力总收入≥1500元；满意度指标：受益对象满意度≥95%","完善产业基地配套基础设施，支持产业发展，吸纳脱贫人口和监测对象参工参运≥2人",2,6,"2025年8-12月","15万元/处","区农业农村和粮食局","普通村"]
[41,"乡村建设行动","蛋鸭养殖基地排水沟","人和乡","布里村","李火珠","新建","布里村","枫树下组","沟700m",12,"衔接资金","产出指标：沟≥700mm；效益指标：受益脱贫人口和监测对象≥6人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥95%","完善产业基地配套基础设施，支持产业发展，吸纳脱贫人口和监测对象参工参运≥2人",2,6,"2025年8-12月","12万元/处","区农业农村和粮食局","普通村"]
[42,"乡村建设行动","农产品加工基地排水沟","人和乡","布里村","李火珠","新建","布里村","枫树下组","沟300m",8,"衔接资金","产出指标：沟≥300m；效益指标：受益脱贫人口和监测对象≥6人，增加劳动力总收入≥800元；满意度指标：受益对象满意度≥96%","项目建设时吸纳脱贫人口和监测对象参工参运≥2人",2,6,"2025年8-12月","8万元/处","区农业农村和粮食局","普通村"]
[43,"乡村建设行动","渠道","人和乡","布里村","李火珠","新建","布里村","布里组","渠道120m\n水泥管120m\n桥板2座",10,"衔接资金","产出指标：渠道≥120m、水泥管≥120m；效益指标：受益脱贫人口和监测对象≥6人，增加劳动力总收入≥1000元；满意度指标：受益对象满意度≥96%","项目建设时吸纳脱贫人口和监测对象参工参运≥2人",6,14,"2025年8-12月","10万元/处","区农业农村和粮食局","普通村"]
[44,"乡村建设行动","村庄整治","人和乡","布里村","李火珠","新建","布里村","枫树下组","沟76m\n砼路面810㎡\n挡土墙长36m",10,"衔接资金","产出指标：沟≥76m、砼路面≥810㎡、挡土墙≥36m；效益指标：受益人口≥311人，其中受益脱贫人口和监测对象≥6人，增加劳动力总收入≥1000元；满意度指标：受益对象满意度≥96%","项目建设时吸纳脱贫人口和监测对象参工参运≥2人",2,6,"2025年8-12月","10万元/处","区农业农村和粮食局","普通村"]
[45,"乡村建设行动","路面硬化","人和乡","棣村村","张保根","新建","棣村村","棣村组","砼路面2080㎡",19.5,"衔接资金","产出指标：砼路面≥2080㎡；效益指标：受益脱贫人口和监测对象≥41人，增加劳动力总收入≥1950元；满意度指标：受益对象满意度≥95%","项目建设时吸纳脱贫人口和监测对象参工参运≥2人",19,41,"2025年8-12月","19.5万元/处","区农业农村和粮食局","区级重点帮扶村"]
[46,"乡村建设行动","路面硬化","人和乡","棣村村","张保根","新建","棣村村","览溪组","砼路335m",14,"衔接资金","产出指标：砼路≥335m；效益指标：受益人口≥715人，其中受益脱贫人口和监测对象≥17人，增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥95%","完善村内基础设施，方便村民出行，吸纳脱贫人口和监测对象参工参运≥2人",8,17,"2025年8-12月","14万元/处","区农业农村和粮食局","区级重点帮扶村"]
[47,"乡村建设行动","路灯","人和乡","观下村","彭小军","新建","观下村","观下组","太阳能路灯51盏",7,"衔接资金","产出指标：太阳能路灯≥51盏；效益指标：受益脱贫人口和监测对象≥34人，增加劳动力总收入≥700元；满意度指标：受益对象满意度≥96%","项目建设时吸纳脱贫人口和监测对象参工参运≥2人",18,34,"2025年8-12月","7万元/处","区农业农村和粮食局","普通村"]
[48,"乡村建设行动","渠道","人和乡","观下村","彭小军","新建","观下村","观下组","渠道550m",12,"衔接资金","产出指标：渠道≥550m，效益指标：受益人口≥486人，其中脱贫人口和监测对象≥34人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥96%","项目建设时吸纳脱贫人口和监测对象参工参运≥2人",18,34,"2025年8-12月","12万元/处","区农业农村和粮食局","普通村"]
[49,"乡村建设行动","渠道","人和乡","辉江村","何红辉","新建","辉江村","辉江组","渠道500m",14,"衔接资金","产出指标：渠道≥500m，效益指标：受益人口≥948人，其中受益脱贫人口和监测对象≥9人，增加劳动力总收入≥1400元；受益对象满意度≥95%","完善农田水利灌溉设施，项目建设吸纳脱贫人口和监测对象参工参运≥2人",5,9,"2025年8-12月","14万元/处","区农业农村和粮食局","区级重点帮扶村"]
[50,"乡村建设行动","渠道","人和乡","辉江村","何红辉","新建","辉江村","姜家坊组","渠道480m",12,"衔接资金","产出指标：渠道≥480m，效益指标：受益人口≥948人，其中受益脱贫人口和监测对象≥9人，增加劳动力总收入≥1200元；受益对象满意度≥95%","完善农田水利灌溉设施，项目建设吸纳脱贫人口和监测对象参工参运≥2人",4,11,"2025年8-12月","12万元/处","区农业农村和粮食局","区级重点帮扶村"]
[51,"乡村建设行动","挡土墙","人和乡","辉江村","何红辉","新建","辉江村","浪溪组","挡土墙200m",12,"衔接资金","产出指标：挡土墙≥200m；效益指标：受益脱贫人口和监测对象≥5人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥95%","项目建设吸纳脱贫人口和监测对象参工参运≥2人",4,5,"2025年8-12月","12万元/处","区农业农村和粮食局","区级重点帮扶村"]
[52,"乡村建设行动","渠道","人和乡","辉江村","何红辉","新建","辉江村","廖家组","渠道500m",13,"衔接资金","产出指标：渠道≥500m；效益指标：受益脱贫人口和监测对象≥5人，增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥95%","完善农田水利灌溉设施，项目建设吸纳脱贫人口和监测对象参工参运≥1人",7,15,"2025年8-12月","13万元/处","区农业农村和粮食局","区级重点帮扶村"]
[53,"乡村建设行动","村庄整治","人和乡","茂江村","何海兵","新建","茂江村","茂江组","砼路160m\n沟290m",13.5,"衔接资金","产出指标：砼路≥160m、沟≥290m；效益指标：受益脱贫人口和监测对象≥38人，增加劳动力总收入≥1350元；满意度指标：受益对象满意度≥95%","项目建设时吸纳脱贫人口和监测对象参工参运≥1人",15,38,"2025年8-12月","13.5万元/处","区农业农村和粮食局","普通村"]
[54,"乡村建设行动","渠道","人和乡","坵宇村","何耐根","新建","坵宇村","坵宇组","渠道450m",13.5,"衔接资金","产出指标：渠道≥450m；效益指标：受益脱贫人口和监测对象≥20人，增加劳动力总收入≥1350元；满意度指标：受益对象满意度≥95%","吸纳脱贫人口和监测对象参工参运≥2人",12,20,"2025年8-12月","13.5万元/处","区农业农村和粮食局","区级重点帮扶村"]
[55,"乡村建设行动","渠道","人和乡","坵宇村","何耐根","新建","坵宇村","塘上组","渠道410m",13,"衔接资金","产出指标：渠道≥410m；效益指标：受益脱贫人口和监测对象≥7人，增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥95%","吸纳脱贫人口和监测对象参工参运≥2人",6,7,"2025年8-12月","13万元/处","区农业农村和粮食局","区级重点帮扶村"]
[56,"乡村建设行动","渠道","人和乡","三山村","丁文君","新建","三山村","三山组","渠道650m",19.5,"衔接资金","产出指标：渠道≥650m；效益指标：受益脱贫人口≥27人，增加劳动力总收入≥1950元；满意度指标：受益对象满意度≥96%","完善农田水利灌溉设施，项目建设吸纳脱贫人口和监测对象参工参运≥2人",15,27,"2025年8-12月","19.5万元/处","区农业农村和粮食局","区级重点帮扶村"]
[57,"乡村建设行动","路灯","人和乡","三山村","丁文君","新建","三山村","上湖组","太阳能路灯39盏",5,"衔接资金","产出指标：太阳能路灯≥39盏；效益指标：受益脱贫人口和监测对象≥7人，增加劳动力总收入≥500元；满意度指标：受益对象满意度≥95%","吸纳脱贫人口和监测对象参工参运≥1人",4,7,"2025年8-12月","5万元/处","区农业农村和粮食局","区级重点帮扶村"]
[58,"乡村建设行动","排水沟","人和乡","穑诞村","何伍芽","新建","穑诞村","西头组","砖沟650m",19,"衔接资金","产出指标：沟≥650m；效益指标：受益人口≥336人，其中受益脱贫人口和监测对象≥11人,增加劳动力收入≥1900元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",8,11,"2025年8-12月","19万元/处","区农业农村和粮食局","“十三五”脱贫村"]
[59,"乡村建设行动","排水沟","人和乡","穑诞村","何伍芽","新建","穑诞村","东头组","砖沟430m",14,"衔接资金","产出指标：沟≥430m；效益指标：受益人口≥336人，其中受益脱贫人口和监测对象≥11人,增加劳动力收入≥1400元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",8,11,"2025年8-12月","14万元/处","区农业农村和粮食局","“十三五”脱贫村"]
[60,"乡村建设行动","路灯","人和乡","田南村","刘友平","新建","田南村","田南、田北、街里组","太阳能路灯78盏",10,"衔接资金","产出指标：太阳能路灯≥78盏；效益指标：受益脱贫人口和监测对象≥21人，增加劳动力总收入≥1000元；满意度指标：受益对象满意度≥95%","项目建设时吸纳脱贫人口和监测对象参工参运≥1人",8,21,"2025年8-12月","10万元/处","区农业农村和粮食局","普通村"]
[61,"乡村建设行动","渠道","人和乡","味塘村","彭满根","新建","味塘村","味塘组","渠道480m",13,"衔接资金","产出指标：渠道≥480m；效益指标：受益脱贫人口和监测对象≥32人，增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥95%","项目建设时吸纳脱贫人口和监测对象参工参运≥1人",19,32,"2025年8-12月","13万元/处","区农业农村和粮食局","区级重点帮扶村"]
[62,"乡村建设行动","路面硬化","人和乡","西村村","何敏","新建","西村村","潘家组","砼路230m",10,"衔接资金","产出指标：砼路≥230m；效益指标：受益人口≥336人，其中受益脱贫人口和监测对象≥6人，增加劳动力收入≥1000元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",3,6,"2025年8-12月","10万元/处","区农业农村和粮食局","区级重点帮扶村"]
[63,"乡村建设行动","村庄整治","人和乡","西村村","何敏","新建","西村村","王家组\n安下组","太阳能路灯70盏\n沟盖板73m\n路面硬化260㎡",16,"衔接资金","产出指标：太阳能路灯≥70盏，路面硬化≥260㎡、沟盖板≥73m；效益指标：受益人口≥95人，其中受益脱贫人口和监测对象≥4人，增加劳动力总收入≥1600元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥1人",3,4,"2025年8-12月","16万元/处","区农业农村和粮食局","区级重点帮扶村"]
[64,"乡村建设行动","挡土墙","人和乡","西村村","何敏","新建","西村村","潘家组","挡土墙160m",10,"衔接资金","产出指标：挡土墙≥160m；效益指标：受益人口≥336人，其中受益脱贫人口和监测对≥象6人，增加劳动力收入≥1000元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",3,6,"2025年8-12月","10万元/处","区农业农村和粮食局","区级重点帮扶村"]
[65,"乡村建设行动","渠道","人和乡","朱家村","吴斌","新建","朱家村","吴家组","渠道326m",8,"衔接资金","产出指标：渠道≥326m；效益指标：受益人口≥246人，其中脱贫人口和监测对象≥6人，增加劳动力总收入≥800元；满意度指标：受益对象满意度≥95%","项目建设时吸纳脱贫人口和监测对象参工参运≥2人",4,6,"2025年8-12月","8万元/处","区农业农村和粮食局","普通村"]
[66,"乡村建设行动","渠道","人和乡","朱家村","吴斌","新建","朱家村","石竹山组","渠道496m",13,"衔接资金","产出指标：渠道≥496m；效益指标：受益人口≥246人，其中脱贫人口和监测对象≥24人，增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥95%","项目建设时吸纳脱贫人口和监测对象参工参运≥2人",12,24,"2025年8-12月","13万元/处","区农业农村和粮食局","普通村"]
[67,"产业发展","慕江村牧草加工厂房","水北镇","慕江村","简平","新建","慕江村","慕江组","加工厂房650㎡",40,"衔接资金","产出指标：加工厂房≥650㎡；效益指标：受益脱贫人口和监测对象≥46人，增加劳动力总收入≥4000元；满意度指标：受益对象满意度≥95%","通过租赁厂房给致富带头人经营，吸纳就业务工，每年增加村集体收入≥2万元，吸纳脱贫人口和监测对象参工参运≥2人",22,46,"2025年8-12月","据实补助","区农业农村和粮食局","区级重点帮扶村"]
[68,"乡村建设行动","村庄整治","水北镇","慕江村","简平","新建","慕江村","罢塘组","挡土墙115m\n入户硬化186m\n太阳能路灯30盏",14,"衔接资金","产出指标：挡土墙≥115m、入户硬化≥186m、太阳能路灯≥30；效益指标：受益脱贫人口和监测对象≥3人，增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",1,3,"2025年8-12月","14万元/处","区农业农村和粮食局","区级重点帮扶村"]
[69,"乡村建设行动","路面硬化","水北镇","北港村","张保生","新建","北港村","圳上组","砼路350m",12.65,"衔接资金","产出指标：砼路≥350m；效益指标：受益人口≥28人，其中受益脱贫人口和监测对象≥28人,增加劳动力收入≥1400元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",12,28,"2025年8-12月","12.65万元/处","区农业农村和粮食局","普通村"]
[70,"乡村建设行动","村庄整治","水北镇","昌下村","敖文鹏","新建","昌下村","李家组","砼路300m\n沟106m",14,"衔接资金","产出指标：砼路≥300m，沟≥106m；效益指标：受益人口≥200人，其中脱贫人口和监测对象≥7人,增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",4,7,"2025年8-12月","14万元/处","区农业农村和粮食局","普通村"]
[71,"乡村建设行动","路面硬化","水北镇","陈家村","何奇渊","新建","陈家村","留土组","砼路480m",14,"衔接资金","产出指标：砼路≥480m；效益指标：受益人口≥230人，其中受益脱贫人口和监测对象≥4人，增加劳动力收入≥1500元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",2,4,"2025年8-12月","14万元/处","区农业农村和粮食局","普通村"]
[72,"乡村建设行动","排水沟","水北镇","黄坑村","傅超","新建","黄坑村","黄坑组","沟630m",16,"衔接资金","产出指标：沟≥630m；效益指标：受益人口≥30人，其中受益脱贫人口和监测对象≥11人,增加劳动力收入≥1600元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥3人",6,11,"2025年8-12月","16万元/处","区农业农村和粮食局","区级重点帮扶村"]
[73,"乡村建设行动","地面硬化","水北镇","黄坑村","傅超","新建","黄坑村","公塘老屋组","地面硬化750m²",6,"衔接资金","产出指标：地面硬化≥750m²；效益指标：受益人口≥30人，其中受益脱贫人口和监测对象≥6人,增加劳动力收入≥600元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥1人",2,5,"2025年8-12月","6万元/处","区农业农村和粮食局","区级重点帮扶村"]
[74,"乡村建设行动","路灯","水北镇","金星村","符建平","新建","金星村","下老港组","太阳能路灯93盏",12,"衔接资金","产出指标：太阳能路灯≥93盏；效益指标：受益脱贫人口和监测对象≥8人,增加劳动力收入≥1200元；满意度指标：受益对象满意度≥96%","吸纳脱贫人口和监测对象参工参运≥3人，助力乡村振兴",6,8,"2025年8-12月","12万元/处","区农业农村和粮食局","区级重点帮扶村"]
[75,"乡村建设行动","村庄整治","水北镇","龙骨村","廖佑平","新建","龙骨村","熊家组","太阳能路灯60盏\n沟300m带盖板\n水泥管80m",16,"衔接资金","产出指标：太阳能路灯≥60盏、沟≥300m、水泥管≥80m；效益指标：受益脱贫人口和监测对象≥10人,增加劳动力总收入≥1600元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥3人",6,9,"2025年8-12月","16万元/处","区农业农村和粮食局","区级重点帮扶村"]
[76,"乡村建设行动","路面硬化","水北镇","楼山村","简勇刚","新建","楼山村","袁家组","砼路445m",14,"衔接资金","产出指标：砼路≥445m；效益指标：受益脱贫人口和监测对象≥2人,增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",2,2,"2025年8-12月","14万元/处","区农业农村和粮食局","区级重点帮扶村"]
[77,"乡村建设行动","路面硬化","水北镇","南陂村","张春保","新建","南陂村","刘家组","路面硬化880㎡\n桥板1块\n太阳能路灯35盏",15,"衔接资金","产出指标：路面硬化≥880㎡、太阳能路灯≥35盏、桥板≥1块；效益指标：受益脱贫人口和监测对象≥7人，增加劳动力总收入≥1500元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥1人",3,7,"2025年8-12月","15万元/处","区农业农村和粮食局","普通村"]
[78,"乡村建设行动","路面硬化","水北镇","南陂村","张春保","新建","南陂村","十年组","路面硬化705m",19,"衔接资金","产出指标：路面硬化≥705m；效益指标：受益脱贫人口和监测对象≥8人，增加劳动力总收入≥1900元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",3,8,"2025年8-12月","19万元/处","区农业农村和粮食局","普通村"]
[79,"乡村建设行动","道路硬化","水北镇","排江村","简毓敏","新建","排江村","排江组","砼路长360m",12,"衔接资金","产出指标：砼路≥360m；效益指标：受益脱贫人口和监测对象≥41人，增加劳动力收入≥1200元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥3人",16,41,"2025年8-12月","12万元/处","区农业农村和粮食局","普通村"]
[80,"乡村建设行动","路面硬化","水北镇","钱圩村","钱新宇","新建","钱圩村","白泉组","砼路540m",16,"衔接资金","产出指标：砼路≥540m；效益指标：受益脱贫人口和监测对象≥6人，增加劳动力总收入≥1600元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥3人",4,6,"2025年8-12月","16万元/处","区农业农村和粮食局","区级重点帮扶村"]
[81,"乡村建设行动","路面硬化","水北镇","琴山村","邓冬生","新建","琴山村","老屋组","砼路430m",12,"衔接资金","产出指标：砼路≥430m；效益指标：受益脱贫人口和监测对象≥12人,增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",4,12,"2025年8-12月","12万元/处","区农业农村和粮食局","“十三五”脱贫村"]
[82,"乡村建设行动","路面硬化","水北镇","琴山村","邓冬生","新建","琴山村","新屋组","砼路355m",14,"衔接资金","产出指标：砼路≥355m；效益指标：受益脱贫人口和监测对象≥11人，增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",4,11,"2025年8-12月","14万元/处","区农业农村和粮食局","“十三五”脱贫村"]
[83,"乡村建设行动","路面硬化","水北镇","上村村","简春金","新建","上村村","西岭组","砼路340m",14,"衔接资金","产出指标：砼路≥340m；效益指标：受益脱贫人口及监测对象≥11人，增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥96%","方便出行，吸纳脱贫人口和监测对象参工参运≥1人，助力乡村振兴",4,11,"2025年8-12月","14万元/处","区农业农村和粮食局","区级重点帮扶村"]
[84,"乡村建设行动","路面硬化","水北镇","石上村","兰花郎","新建","石上村","上兰组","砼路445m",14,"衔接资金","产出指标：砼路≥445m；效益指标：受益脱贫人口和监测对象≥14人,增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥4人",5,14,"2025年8-12月","14万元/处","区农业农村和粮食局","普通村"]
[85,"乡村建设行动","村庄整治","水北镇","水北村","敖林道","新建","水北村","都宪第组","太阳能路灯30盏，吸水砖185㎡，沟180m",10,"衔接资金","产出指标：太阳能路灯≥30盏、吸水砖≥185㎡、沟≥180m；\n效益指标：受益脱贫人口和监测对象≥14人，增加劳动力收入≥1000元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥4人",7,14,"2025年8-12月","10万元/处","区农业农村和粮食局","普通村"]
[86,"乡村建设行动","路面硬化","水北镇","潭江村","胡草根","新建","潭江村","胡家组","砼路430m",14,"衔接资金","产出指标：砼路≥430m；效益指标：受益脱贫人口和监测对象≥14人,增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥3人",7,14,"2025年8-12月","14万元/处","区农业农村和粮食局","区级重点帮扶村"]
[87,"乡村建设行动","村庄整治","水北镇","潭江村","胡草根","新建","潭江村","张家组","太阳能路灯37盏        砖沟60m",8,"衔接资金","产出指标：太阳能路灯≥37盏，砖沟≥60m，效益指标：受益脱贫人口和监测对象≥6人,增加劳动力总收入≥800元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人,增加劳动力总收入≥0.1万元",3,6,"2025年8-12月","8万元/处","区农业农村和粮食局","区级重点帮扶村"]
[88,"乡村建设行动","路灯","水北镇","伍塘村","傅金香","新建","伍塘村","熊坑组","太阳能路灯93盏",12,"衔接资金","产出指标：太阳能路灯≥93盏；效益指标：受益脱贫人口和监测对象≥10人,增加劳动力总收入≥0.11万元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥3人",3,10,"2025年8-12月","12万元/处","区农业农村和粮食局","普通村"]
[89,"乡村建设行动","村庄整治","水北镇","泉塘村","桂雪勇","新建","泉塘村","桂家三组","砖沟330m\n硬化600㎡",13,"衔接资金","产出指标：硬化面积≥600㎡，沟≥330m；效益指标：受益人口≥44人，其中脱贫人口和监测对象≥8人,增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥96%","项目建设吸纳受益脱贫人口和监测对象参工参运≥3人",13,44,"2025年8-12月","13万元/处","区农业农村和粮食局","市级重点帮扶村"]
[90,"乡村建设行动","村庄整治","下村镇","罗家边村","黄二根","新建","罗家边村","月形里组","砼路270m\n沟128m\n太阳能路灯20盏",14,"衔接资金","产出指标：砼路≥270m、沟≥128m、太阳能路灯≥20盏；效益指标：受益人口≥212人，其中脱贫人口和监测对象≥1人，增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥95%","完善村庄基础设施，吸纳脱贫人口参工参运≥1人，助力乡村振兴",1,1,"2025年8-12月","14万元/处","区农业农村和粮食局","普通村"]
[91,"乡村建设行动","路灯","下村镇","大桥村","彭海民","新建","大桥村","牛湾垱组","太阳能路灯62盏",8,"衔接资金","产出指标：太阳能路灯≥62盏；效益指标：受益人口≥206人、其中脱贫人口和监测对象≥1人，增加劳动力总收入≥800元；满意度指标：受益对象满意度≥93%。","项目建设吸纳脱贫人口参工参运≥2人",1,1,"2025年8-12月","8万元/处","区农业农村和粮食局","区级重点帮扶村"]
[92,"乡村建设行动","村庄整治","下村镇","袁家村","邱细宝","新建","袁家村","员岭组","沟186m\n挡土墙长57m\n砼路90m\n吸水砖288㎡\n波纹管5m\n污水处理池3个",14.5,"衔接资金","产出指标：沟≥186m，挡土墙≥57m、砼路≥90m、吸水砖≥288㎡、波纹管≥5m、污水处理池≥3个；效益指标：受益人口≥110人，其中脱贫人口≥3人，增加劳动力总收入≥1450元；满意度指标：受益对象满意度95%","项目建设吸纳脱贫人口参工参运≥2人",2,3,"2025年8-12月","14.5万元/处","区农业农村和粮食局","普通村"]
[93,"乡村建设行动","路灯","下村镇","袁家村","邱细宝","新建","袁家村","高家组","太阳能路灯54盏",7,"衔接资金","产出指标：太阳能路灯≥54盏；效益指标：受益人口≥419人，其中受益脱贫户≥20人，增加劳动力总收入≥700元；满意度指标：受益对象满意度≥95%","方便夜间出行，吸纳脱贫人口和监测对象参工参运≥2人，助力乡村振兴",6,20,"2025年8-12月","7万元/处","区农业农村和粮食局","普通村"]
[94,"乡村建设行动","路面硬化","下村镇","下住村","黄友珠","新建","下住村","下樟坡组","砼路478m",14,"衔接资金","产出指标：砼路≥478m；效益指标：受益人口≥122人，其中受益脱贫人口≥2人，增加劳动力总收入≥1400万元；满意度指标：受益脱贫人口满意度96%。","吸纳脱贫人口受益脱贫人口参工参运≥1人，助力乡村振兴",1,2,"2025年8-12月","14万元/处","区农业农村和粮食局","普通村"]
[95,"乡村建设行动","路灯","下村镇","下住村","黄友珠","新建","下住村","新屋组","太阳能路灯39盏",5,"衔接资金","产出指标：太阳能路灯≥39盏；效益指标：受益人口≥96人，其中脱贫人口及监测对象≥2人，增加劳动力总收入≥500元；满意度指标：受益对象满意度≥95%","方便夜间出行，吸纳脱贫人口和监测对象参工参运≥1人，助力乡村振兴",1,2,"2025年8-12月","5万元/处","区农业农村和粮食局","普通村"]
[96,"乡村建设行动","路面硬化","下村镇","杭桥村","张迎春","新建","杭桥村","新王家山组","砼路面1150㎡\n太阳能路灯30盏",14,"衔接资金","产出指标：砼路面≥1150㎡、太阳能路灯≥30盏；项目验收合格率100%，受益人口≥99人，其中受益脱贫人口≥1人，增加劳动力总收入≥1400元,；满意度指标：受益对象满意度≥95%。","完善村庄基础设施，吸纳脱贫人口参工参运≥2人，助力乡村振兴",1,1,"2025年8-12月","14万元/处","区农业农村和粮食局","区级重点帮扶村"]
[97,"乡村建设行动","路面硬化","下村镇","高站村","张志华","新建","高站村","垱上组","沟72m\n波纹管约217m\n砼路136m\n地面硬化647㎡",14.5,"衔接资金","产出指标：沟≥72m、波纹管≥217m、砼路≥136m、地面硬化≥647㎡；项目验收合格率100%，效益指标：受益人口≥55人，其中脱贫人口≥1人，增加劳动力总收入≥1450元；满意度指标：受益对象满意度≥95%","完善村庄基础设施，项目建设吸纳脱贫人口参工参运≥2人",1,1,"2025年8-12月","14.5万元/处","区农业农村和粮食局","普通村"]
[98,"乡村建设行动","路灯","下村镇","南村村","廖圳古","新建","南村村","土坎组","太阳能路灯39盏",5,"衔接资金","产出指标：太阳能路灯≥39盏；效益指标：受益人口≥390人，其中脱贫人口≥4人，增加劳动力收入≥500元；满意度指标：受益对象满意度≥95%","方便夜间出行，吸纳脱贫人口参工参运≥1人，助力乡村振兴",1,2,"2025年8-12月","5万元/处","区农业农村和粮食局","普通村"]
[99,"乡村建设行动","路灯","下村镇","南村村","廖圳古","新建","南村村","言家组","太阳能路灯47盏",6,"衔接资金","产出指标：太阳能路灯≥47盏；效益指标：受益人口≥190人，其中脱贫人口≥4人,增加劳动力收入≥600元；满意度指标：受益对象满意度≥95%","方便夜间出行，吸纳脱贫人口参工参运≥1人，助力乡村振兴",1,4,"2025年8-12月","6万元/处","区农业农村和粮食局","普通村"]
[100,"乡村建设行动","村庄整治","下村镇","千秋岭村","陈和平","新建","千秋岭村","老屋组","沟178m\n路面硬化1148㎡",14,"衔接资金","产出指标：沟≥178m、路面硬化≥1148㎡；效益指标：受益人口≥408人，其中脱贫人口和监测对象≥12人，增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥95%","完善村庄基础设施，吸纳脱贫人口参工参运≥1人，助力乡村振兴",6,12,"2025年8-12月","14万元/处","区农业农村和粮食局","区级重点帮扶村"]
[101,"乡村建设行动","路灯","下村镇","虹桥村","吴志勇","新建","虹桥村","脑上组、简坑组","太阳能路灯54盏",7,"衔接资金","产出指标：太阳能路灯≥54盏；项目验收合格率100%；效益指标：受益脱贫人口及监测对象≥11人，增加劳动力总收入≥700元；满意度指标：受益对象满意度≥92%","方便夜间出行，吸纳脱贫人口和监测对象参工参运≥1人，助力乡村振兴",5,11,"2025年8-12月","7万元/处","区农业农村和粮食局","普通村"]
[102,"乡村建设行动","路面硬化","下村镇","江东村","胡仁根","新建","江东村","胡家组","砼路306m",12,"衔接资金","产出指标：砼路≥306m；受益人口≥298人，其中受益脱贫户≥4人,增加劳动力收入≥1200元；满意度指标：受益对象满意度≥93%","完善村庄基础设施，吸纳脱贫人口2人参工参运，助力乡村振兴",11,22,"2025年8-12月","12万元/处","区农业农村和粮食局","区级重点帮扶村"]
[103,"乡村建设行动","渠道","下村镇","花堆村","吴义","新建","花堆村","北宅组","渠道420m",14,"衔接资金","产出指标：渠道≥420m；效益指标：受益人口≥750人，其中受益脱贫人口和监测对象≥10人,增加劳动力收入≥1400元；满意度指标：受益对象满意度≥98%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",5,10,"2025年8-12月","14万元/处","区农业农村和粮食局","区级重点帮扶村"]
[104,"乡村建设行动","渠道","下村镇","花堆村","吴义","新建","花堆村","先锋组","渠道435m\n桥涵1个",15,"衔接资金","产出指标：渠道≥435m；效益指标：受益人口≥560人，其中受益脱贫人口和监测对象≥14人，增加劳动力收入≥1500元；满意度指标：受益对象满意度≥92%","完善村庄基础设施，吸纳受益脱贫人口和监测对象参工参运1人",6,14,"2025年8-12月","15万元/处","区农业农村和粮食局","区级重点帮扶村"]
[105,"乡村建设行动","路面硬化","下村镇","下村村","吴红兵","新建","下村村","胡家组","砼路529m",12,"衔接资金","产出指标：砼路≥529m；效益指标：受益人口≥1838人，其中受益脱贫人口和监测对象≥6人，增加劳动力收入≥1200元；满意度指标：受益对象满意度≥95%","完善村庄基础设施，吸纳脱贫人口参工参运≥2人，助力乡村振兴",2,6,"2025年8-12月","12万元/处","区农业农村和粮食局","区级重点帮扶村"]
[106,"乡村建设行动","渠道","下村镇","高升村","罗小明","新建","高升村","新罗坑组","渠道980m",12,"衔接资金","产出指标：渠道≥980m；效益指标：受益人口≥283人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥95%","完善村庄基础设施，吸纳脱贫人口参工参运≥2人，助力乡村振兴",1,1,"2025年8-12月","12万元/处","区农业农村和粮食局","普通村"]
[107,"乡村建设行动","路灯","下村镇","步桥村","李峰","新建","步桥村","步桥组","太阳能路灯93盏",12,"衔接资金","产出指标：太阳能路灯≥93盏；效益指标：受益人口≥503人，其中脱贫人口及监测对象≥9人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥95%","方便夜间出行，吸纳脱贫人口参工参运≥2人，助力乡村振兴",5,9,"2025年8-12月","12万元/处","区农业农村和粮食局","普通村"]
[108,"乡村建设行动","路面硬化","下村镇","步桥村","李峰","新建","步桥村","店里组","砼路368m",12.5,"衔接资金","产出指标：砼路≥368m；效益指标：受益人口≥256人，其中受益脱贫户≥1人，增加劳动力总收入≥1250元；满意度指标：受益对象满意度≥93%","完善村庄基础设施，吸纳脱贫人口参工参运≥1人，助力乡村振兴",1,1,"2025年8-12月","12.5万元/处","区农业农村和粮食局","普通村"]
[109,"乡村建设行动","果蔬种植基地产业路","新溪乡","城头村","刘慧龙","新建","城头村","杨家组","产业路430m",14,"衔接资金","产出指标：产业路≥430m；效益指标：受益人口≥80人，其中脱贫人口和监测对象≥6人,增加劳动力收入≥1400元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥1人，增加劳动力总收入≥1400元",2,6,"2025年8-12月","14万元/处","区农业农村和粮食局","市级重点帮扶村"]
[110,"乡村建设行动","村庄整治","新溪乡","复兴村","傅江平","新建","复兴村","邹家组","太阳能灯60盏\n砼路130m",12.5,"衔接资金","产出指标：太阳能灯≥60盏、砼路≥130m；效益指标：受益人口≥460人，其中受益脱贫人口和监测对象≥5人，增加劳动力收入≥1250元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人,增加劳动力总收入≥1250元",2,5,"2025年8-12月","12.5万元/处","区农业农村和粮食局","普通村"]
[111,"乡村建设行动","黄土坑路面硬化","新溪乡","后溪村","曾洪庆","新建","后溪村","后溪组","砼路370m",13.5,"衔接资金","产出指标：砼路≥370m；效益指标：受益人口≥600人，其中受益脱贫人口和监测对象≥12人,增加劳动力收入≥1350元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人,增加劳动力总收入≥1350元",4,12,"2025年8-12月","13.5万元/处","区农业农村和粮食局","区级重点帮扶村"]
[112,"乡村建设行动","排水沟","新溪乡","均溪村","龚欠如","新建","均溪村","下龚组","沟400m",14,"衔接资金","产出指标：沟≥400m；效益指标：受益人口≥600人，其中受益脱贫人口和监测对象≥15人，增加劳动力收入≥1400元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥1人,增加劳动力总收入≥1400元",5,15,"2025年8-12月","14万元/处","区农业农村和粮食局","普通村"]
[113,"乡村建设行动","路面硬化","新溪乡","龙尾洲村","黄伟伟","新建","龙尾洲村","龙尾洲组","砼路305m\n排水管160m",13,"衔接资金","产出指标：砼路≥305m、排水管≥160m；效益指标：受益人口≥355人，其中脱贫人口和监测对象≥48人，增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人，增加劳动力总收入≥1300元",17,48,"2025年8-12月","13万元/处","区农业农村和粮食局","区级重点帮扶村"]
[114,"乡村建设行动","路面硬化","新溪乡","明星村","陈涛","新建","明星村","杨家组","砼路350m\n太阳能路灯10盏",14,"衔接资金","产出指标：砼路≥350m、太阳能路灯≥10盏；效益指标：受益人口≥115人，其中脱贫人口和监测对象≥39人，增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥95%","完善村庄道路建设，方便村民出行，吸纳脱贫人口和监测对象参工参运≥2人，增加劳动力总收入≥1400元",12,39,"2025年8-12月","14万元/处","区农业农村和粮食局","区级重点帮扶村"]
[115,"乡村建设行动","村庄整治","新溪乡","泗溪村","刘小亮","新建","泗溪村","钟溪组","沟200m\n太阳能路灯50盏",13,"衔接资金","产出指标：沟≥200m，太阳能路灯≥50盏；效益指标：受益人口≥200人，其中脱贫人口和监测对象≥4人,增加劳动力收入≥1300元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥1人，增加劳动力总收入≥1300元",2,4,"2025年8-12月","13万元/处","区农业农村和粮食局","区级重点帮扶村"]
[116,"乡村建设行动","路面硬化","新溪乡","珠坑村","敖春牙","新建","珠坑村","珠坑组","砼路450m",14,"衔接资金","产出指标：砼路≥450m；效益指标：受益人口≥600人，其中受益脱贫人口和监测对象≥34人,增加劳动力收入≥1400元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人,增加劳动力总收入≥1400元",12,34,"2025年8-12月","14万元/处","区农业农村和粮食局","普通村"]
[117,"乡村建设行动","花卉苗木基地产业路","姚圩镇",null,"张泽慧","新建","裴港村","西岸组","产业路3000㎡",47,"衔接资金","产出指标：产业路≥3000㎡；效益指标：受益脱贫人口和监测对象≥87人,增加劳动力总收入≥4700元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",41,87,"2025年8-12月","47万元/处","区农业农村和粮食局"]
[118,"乡村建设行动","蜜桔产业园产业路","姚圩镇",null,"张泽慧","新建","姚圩村","力上组","产业路1325㎡含碎石垫层",20,"衔接资金","产出指标：产业路≥1325㎡；效益指标：受益脱贫人口和监测对象≥5人,增加劳动力总收入≥2000元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",5,5,"2025年8-12月","20万元/处","区农业农村和粮食局"]
[119,"乡村建设行动","蜜桔产业园配套基础设施项目","姚圩镇",null,"张泽慧","新建","姚圩村","力上组","片石挡墙103m\n砖墙168m\n沟168m",30,"衔接资金","产出指标：片石挡墙≥103m、砖墙≥168m、沟≥168m；效益指标：受益脱贫人口和监测对象≥5人,增加劳动力总收入≥3000元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",5,5,"2025年8-12月","30万元/处","区农业农村和粮食局"]
[120,"乡村建设行动","道路加宽","姚圩镇","裴港村","裴金保","新建","裴港村","西岸组","道路加宽840m",14,"衔接资金","产出指标：道路加宽≥840m，效益指标：受益人口≥1280人，其中脱贫人口和监测对象≥17人，增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",13,17,"2025年8-12月","14万元/处","区农业农村和粮食局","普通村"]
[121,"乡村建设行动","道路加宽","姚圩镇","中元村","何梅芽","新建","中元村","车下组","道路加宽600m*1.2m*0.18m",8,"衔接资金","产出指标：道路加宽≥600m；效益指标：受益脱贫人口和监测对象≥8人，增加劳动力总收入≥800元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",3,8,"2025年8-12月","8万元/处","区农业农村和粮食局","区级重点帮扶村"]
[122,"乡村建设行动","路面硬化","姚圩镇","湾里村","彭卫卫","新建","湾里村","彭家二组","砼路长394m宽3.2m厚0.15m",11,"衔接资金","产出指标：砼路≥394m；效益指标：受益人口≥418人，其中脱贫人口和监测对象≥4人,增加劳动力总收入1100元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",3,4,"2025年8-12月","11万元/处","区农业农村和粮食局","普通村"]
[123,"乡村建设行动","路面硬化","姚圩镇","湾里村","彭卫卫","新建","湾里村","彭家三组","砼路长287m宽5m厚0.18m",14,"衔接资金","产出指标：砼路≥287m；效益指标：受益人口≥418人，其中脱贫人口和监测对象≥4人,增加劳动力总收入1400元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",3,4,"2025年8-12月","14万元/处","区农业农村和粮食局","普通村"]
[124,"乡村建设行动","路面硬化","姚圩镇","刘家村","刘香芽","新建","刘家村","刘家组","砼路400m*3.5m*0.18m",14,"衔接资金","产出指标：砼路≥400m，效益指标：受益人口≥1280人，其中脱贫人口和监测对象≥63人,增加劳动力收入≥1400元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",32,63,"2025年8-12月","14万元/处","区农业农村和粮食局","“十四五”省级重点帮扶村"]
[125,"乡村建设行动","路面硬化","姚圩镇","姚家村","姚伟","新建","姚家村","章家组","砼路400m*3.5m*0.18m",14,"衔接资金","产出指标：砼路≥400m；效益指标：受益脱贫人口和监测对象≥3人，增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥1人",3,8,"2025年8-12月","14万元/处","区农业农村和粮食局","普通村"]
[126,"乡村建设行动","排水管","姚圩镇","年家村","廖小玉","新建","年家村","下垱组","波纹管500m",12,"衔接资金","产出指标：波纹管≥500m； 效益指标：受益脱贫人口和监测对象≥10人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥1人",4,10,"2025年8-12月","12万元/处","区农业农村和粮食局","区级重点帮扶村"]
[127,"乡村建设行动","路面硬化","姚圩镇","南河村","温小根","新建","南河村","老屋组","砼路335m",14,"衔接资金","产出指标：砼路≥335m；效益指标：受益人口≥19人，增加劳动力收入≥1400元；满意度指标：受益对象满意度≥95%。","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",10,19,"2025年8-12月","14万元/处","区农业农村和粮食局","区级重点帮扶村"]
[128,"乡村建设行动","道路硬化","姚圩镇","新宋村","宋林根","新建","新宋村","老宋组","砼路200m",7.5,"衔接资金","产出指标：砼路≥200m；效益指标：受益脱贫人口和监测对象≥101人，增加劳动力总收入≥750元；满意度指标：受益对象满意度≥95%","方便出行，吸纳脱贫人口和监测对象参工参运≥2人，助力增收",52,101,"2025年8-12月","7.5万元/处","区农业农村和粮食局","区级重点帮扶村"]
[129,"乡村建设行动","路面硬化","姚圩镇","万全村","艾卫忠","新建","万全村","艾家组","砼路395m",14.5,"衔接资金","产出指标：砼路≥395m；效益指标：受益人口≥992人，其中脱贫人口和监测对象≥44人，增加劳动力总收入≥1450元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",23,44,"2025年8-12月","14.5万元/处","区农业农村和粮食局","区级重点帮扶村"]
[130,"乡村建设行动","路灯","姚圩镇","万全村","艾卫忠","新建","万全村","艾家组","太阳能路灯58盏",7.5,"衔接资金","产出指标：太阳能路灯≥58盏，效益指标：受益人口≥992人，其中脱贫人口和监测对象≥44人，增加劳动力总收入≥750元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",23,44,"2025年8-12月","7.5万元/处","区农业农村和粮食局","区级重点帮扶村"]
[131,"乡村建设行动","路面硬化","姚圩镇","蒋家村","蒋华儿","新建","蒋家村","湖州组","砼路200m",10,"衔接资金","产出指标：砼路≥200m；效益指标：受益脱贫人口和监测对象≥101人，增加劳动力总收入≥1000元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",5,9,"2025年8-12月","10万元/处","区农业农村和粮食局","区级重点帮扶村"]
[132,"乡村建设行动","排水沟","姚圩镇","河埠村","张艳平","新建","河埠村","张家组","沟380m",16,"衔接资金","产出指标：沟≥380m；效益指标：受益人口≥948人，其中脱贫人口和监测对象≥24人，增加劳动力总收入≥1600元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",13,24,"2025年8-12月","16万元/处","区农业农村和粮食局","“十三五”脱贫村"]
[133,"乡村建设行动","路面硬化","姚圩镇","河埠村","张艳平","新建","河埠村","刘家组","路面硬化330m²\n波纹管50m",6,"衔接资金","产出指标：路面硬化≥330m²、波纹款≥50m；效益指标：受益人口≥948人，其中脱贫人口和监测对象≥4人,增加劳动力总收入≥600元；满意度指标：受益对象满意度95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",1,4,"2025年8-12月","6万元/处","区农业农村和粮食局","“十三五”脱贫村"]
[134,"乡村建设行动","村内排水沟","姚圩镇","河埠村","张艳平","新建","河埠村","艾家组","沟160m带盖板",8,"衔接资金","产出指标：沟≥160m；效益指标：受益脱贫人口和监测对象≥29人，增加劳动力总收入≥800元，受益对象满意度≥95%","项目建设时吸纳脱贫人口和监测对象参工参运≥2人",14,27,"2025年8-12月","8万元/处","区农业农村和粮食局","“十三五”脱贫村"]
[135,"乡村建设行动","道路加宽","姚圩镇","河埠村","张艳平","新建","河埠村","艾家组","砼路面1247㎡\n路沿石467m\n检查井21个",13,"衔接资金","产出指标：砼路面≥1247㎡、路沿石≥467m；效益指标：受益脱贫人口和监测对象≥29人，增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥95%","项目建设吸纳参工参运脱贫人口和监测对象≥2人",16,29,"2025年8-12月","13万元/处","区农业农村和粮食局","“十三五”脱贫村"]
[136,"乡村建设行动","路面硬化","姚圩镇","高湖村","龚磊平","新建","高湖村","下房组","砼路340m",14,"衔接资金","产出指标：砼路≥340m；效益指标：受益人口≥1571人，其中脱贫人口和监测对象≥15人,增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",8,15,"2025年8-12月","14万元/处","区农业农村和粮食局","区级重点帮扶村"]
[137,"乡村建设行动","路面硬化","姚圩镇","姚圩村","艾林玲","新建","姚圩村","宁家组","砼路400m",14,"衔接资金","产出指标：砼路≥400m；效益指标：受益脱贫人口和监测对象≥15人,增加劳动力总收入≥1400元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",5,12,"2025年8-12月","14万元/处","区农业农村和粮食局","普通村"]
[138,"乡村建设行动","路灯","珠珊镇","丰溪村","胡军","新建","丰溪村","丰溪组","太阳能路灯97盏",12.5,"衔接资金","产出指标：太阳能路灯≥97盏；效益指标：受益人口≥900人，其中脱贫人口和监测对象≥36人，增加劳动力收入≥1250元；满意度指标：受益对象满意度≥95%","方便出行，吸纳脱贫人口参工参运≥1人",13,36,"2025年8-12月","12.5万元/处","区农业农村和粮食局","区级重点帮扶村"]
[139,"乡村建设行动","渠道","珠珊镇","洋津村","罗刚","新建","洋津村","宗家组","渠道285m",13,"衔接资金","产出指标：渠道≥285m；效益指标：受益脱贫人口和监测对象≥103人、增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥93%","吸纳脱贫人口参工参运≥2人",45,103,"2025年8-12月","13万元/处","区农业农村和粮食局","普通村"]
[140,"乡村建设行动","路面硬化","珠珊镇","垱上村","胡林泉","新建","垱上村","鄱头组","砼路100m\n道路加宽500m",12,"衔接资金","产出指标：砼路≥100m、道路加宽≥500m；效益指标：受益脱贫和监测对象≥12人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥95%","方便出行，吸纳脱贫人口和监测对象参工参参运≥1人，助力脱贫户增收",5,12,"2025年8-12月","12万元/处","区农业农村和粮食局","区级重点帮扶村"]
[141,"乡村建设行动","路面硬化","珠珊镇","花田村","廖\n志平","新建","花田村","花田组","砼路480m",15,"衔接资金","产出指标：砼路≥480m；效益指标：受益脱贫和监测对象≥19人，增加劳动力总收入≥1500元；满意度指标：受益对象满意度≥95%","方便出行，吸纳纳脱贫人口和监测对象参工参运≥2人，助力脱贫户增收",8,19,"2025年8-12月","15万元/处","区农业农村和粮食局","普通村"]
[142,"乡村建设行动","路灯","珠珊镇","鹏湖村","喻国安","新建","鹏湖村","上村组","太阳能路灯62盏",8,"衔接资金","产出指标：太阳能路灯≥62盏；效益指标：受益脱贫人口和监测对象≥2人，增加劳动力总收入≥800元；满意度指标：受益对象满意度≥95%","改善人居环境，吸纳脱贫人口参工参运≥1人",1,2,"2025年8-12月","8万元/处","区农业农村和粮食局","区级重点帮扶村"]
[143,"乡村建设行动","路灯","珠珊镇","沙头村","胡永军","新建","沙头村","弯里组","太阳能路灯77盏",10,"衔接资金","产出指标：太阳能路灯≥77盏；效益指标：受益脱贫人口和监测对象≥78人，增加劳动力总收入≥1000元；满意度指标：受益对象满意度≥95%","方便村民夜间出行，吸纳脱贫人口和监测对象参工参运≥2人",23,78,"2025年8-12月","10万元/处","区农业农村和粮食局","区级重点帮扶村"]
[144,"乡村建设行动","路面硬化","珠珊镇","纱笼村","胡腾彪","新建","纱笼村","纱笼组","砼路141m\n地面硬化1300m²",12,"衔接资金","产出指标：砼路≥140m；地面硬化≥1300m²；效益指标：受益脱贫和监测对象≥14人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥95%","方便出行，吸纳脱贫人口和监测对象参工参参运≥1人",4,14,"2025年8-12月","12万元/处","区农业农村和粮食局","普通村"]
[145,"乡村建设行动","地面硬化","珠珊镇","潭口村","胡慧敏","新建","潭口村","潭口组","地面硬化1840m²\n波纹管100m",20,"衔接资金","产出指标：砼地面≥1840m²、波纹管≥100m；效益指标：受益脱贫和监测对象≥31人，增加劳动力总收入≥2000元；满意度指标：受益对象满意度≥95%","方便出行，吸纳脱贫人口和监测对象参工参参运≥2人",10,31,"2025年8-12月","20万元/处","区农业农村和粮食局","普通村"]
[146,"乡村建设行动","村庄整治","珠珊镇","洲下村","胡宁","新建","洲下村","城塘口组","太阳能路灯≥30盏\n沟410m\n路面硬化1125㎡",17.5,"衔接资金","产出指标：太阳能路≥30盏、沟≥410m、路面硬化≥1125㎡；效益指标：受益人口≥190人，其中脱贫人口和监测对象≥4人，增加劳动力总收入≥1750元；满意度指标：受益对象满意度≥95%","项目建设吸纳受益脱贫人口和监测对象参工参运≥1人",4,4,"2025年8-12月","17.5万元/处","区农业农村和粮食局","区级重点帮扶村"]
[147,"乡村建设行动","路灯","珠珊镇","庄上村","丁军勇","新建","庄上村","彭家组","太阳能路灯100盏",13,"衔接资金","产出指标：太阳能路灯≥100盏；效益指标：受益脱贫人口和监测对象≥61人，增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥95%","方便村民夜间出行，吸纳脱贫人口和监测对象参工参运≥2人",18,61,"2025年8-12月","13万元/处","区农业农村和粮食局","区级重点帮扶村"]
[148,"产业发展","肉牛养殖厂房","马洪办","马洪办","龚桂菊","新建","山南村","山南组","肉牛养殖厂房2600㎡",94,"衔接资金","产出指标：肉牛养殖厂房面积≥2600㎡；效益指标：产业带动脱贫人口和监测对象就业≥1人，受益脱贫人口和监测对象数≥562人，增加劳动力总收入≥9400元；满意度指标：受益对象满意度≥95%，经营主体满意度≥95%","吸纳脱贫人口参工参运≧1人，受益脱贫人口和监测对象户均增收≧200元/年",232,562,"2025年8-12月","据实补助","区农业农村和粮食局",null,"高新区"]
[149,"乡村建设行动","肉牛养殖产业配电项目","马洪办","马洪办","龚桂菊","新建","山南村","山南组","新建250KW变压器及电缆",15,"衔接资金","产出指标：250KW变压器≥1台，效益指标：受益脱贫人口和监测对象≥562人，增加劳动力总收入≥1500元；满意度指标：受益对象满意度≥95%，经营主体满意度≥95%","吸纳脱贫人口参工参运≧1人，受益脱贫人口和监测对象户均增收≧200元/年。",232,562,"2025年8-12月","15万元/处","区农业农村和粮食局",null,"高新区"]
[150,"产业发展","东港鹌鹑厂光伏","马洪办","马洪办","龚桂菊","新建","东港村","枫树下组","新建光伏电站容量128.7KW",28.5,"衔接资金","产出指标：光伏电站容量≥128.7KW；效益指标：产业带动脱贫人口和监测对象就业≥1人、受益脱贫人口和监测对象≥562人，增加劳动力总收入≥2850元；满意度指标：受益对象满意度≥95%","项目建设时吸纳脱贫人口参工参运≧1人，建成后受益脱贫人口和监测对象户均增收≧200元/年",232,562,"2025年8-12月","据实补助","高新区经济发展局",null,"高新区"]
[151,"乡村建设行动","易博鹌鹑养殖产业基础设施项目","马洪办","马洪办","龚桂菊","新建","白沙桥村","白沙桥组","砼围挡468m",11.8,"衔接资金","产出指标：围挡≥468m；效益指标：受益脱贫人口和监测对象≥562人，增加劳动力总收入≥1180元；满意度指标：受益对象满意度≥95%","有效解决产业安全问题，从而推动产业发展，项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",232,562,"2025年8-12月","11.8万元/处","区农业农村和粮食局",null,"高新区"]
[152,"乡村建设行动","母牛养殖产业基地护坡","马洪办","马洪办","龚桂菊","新建","南岭村","书坑组","砼护坡748.5㎡\n沟124m",13,"衔接资金","产出指标：护坡≥748.5㎡、沟≥124m；效益指标：受益脱贫人口和监测对象≥562人，增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥95%","有效解决产业安全问题，从而推动产业项目建设，项目建设吸纳受益脱贫人口和监测对象参工参运≥2人",232,562,"2025年8-12月","13万元/处","区农业农村和粮食局",null,"高新区"]
[153,"乡村建设行动","挡墙","马洪办","南岭村","华小强","新建","南岭村","书坑组","砖砌挡墙25m\n混凝土挡墙140m",35,"衔接资金","产出指标：挡墙≥165m；效益指标：受益脱贫人口和监测对象≥12人，增加劳动力总收入≥3500元；满意度指标：受益对象满意度≥95%","完善村庄建设，项目建设时吸纳脱贫人口和监测对象参工参运≥2人",232,562,"2025年8-12月","35万元/处","区农业农村和粮食局","区级重点帮扶村","高新区"]
[154,"乡村建设行动","道路","马洪办","堆李村","李云","新建","堆李村","路塘组","拆除破损砼路面249㎡\n砼路面968㎡",12,"衔接资金","产出指标：砼路面≥968㎡；效益指标：受益脱贫人口和监测对象≥6人，增加劳动力总收入≥1200元；满意度指标：受益对象满意度≥95%","方便村民出行，吸纳脱贫人口和监测对象参工参运≥2人",5,12,"2025年8-12月","12万元/处","区农业农村和粮食局","区级重点帮扶村","高新区"]
[155,"乡村建设行动","村庄整治","马洪办","王家下村","廖志均","新建","王家下村","肖家陂组","砖砌挡墙122m\n砖沟105m\n踏步30㎡",8.7,"衔接资金","产出指标：砖砌挡墙≥122m、沟≥105m、踏步≥30㎡；效益指标：受益脱贫人口和监测对象≥7人，增加劳动力总收入≥870元；满意度指标：受益对象满意度≥95%","完善村庄环境建设，项目建设时吸纳脱贫人口和监测对象参工参运≥2人",3,7,"2025年8-12月","8.7万元/处","区农业农村和粮食局","区级重点帮扶村","高新区"]
[156,"乡村建设行动","村庄整治","马洪办","堆王村","王卫平","新建","堆王村","禾井垱组","砼路220m\n沟220m\n雨水管40m",17,"衔接资金","产出指标：砼路≥220m、沟≥220m、雨水管≥40m；效益指标：受益脱贫人口和监测对象≥38人，增加劳动力总收入≥1700元；满意度指标：受益对象满意度≥95%","完善村庄环境建设，项目建设时吸纳脱贫人口和监测对象参工参运≥2人",15,38,"2025年8-12月","17万元/处","区农业农村和粮食局","区级重点帮扶村","高新区"]
[157,"乡村建设行动","村庄整治","水西镇","丁下村","刘庆庆","新建","丁下村","中房组","路面硬化2400㎡\n沟400m",31,"衔接资金","产出指标：路面硬化≥2400㎡、沟≥400m，项目（工程）验收合格率100%，项目（工程）完成及时率100%，工程设计使用年限≥5年；效益指标：受益脱贫人口和监测对象≧15人，增加劳动力收入≥3100元；满意度指标：受益对象满意度≧95%","项目建设时吸纳脱贫人口参工参运≥1人",7,15,"2025年8-12月","31万元/处","区农业农村和粮食局","普通村","高新区"]
[158,"乡村建设行动","村庄整治","水西镇","汉元村","阮建","新建","汉元村","汉元组","路面硬化780㎡\n沟80m",16,"衔接资金","产出指标：路面硬化≥780㎡、沟≥80m、项目验收合格率100%、项目完成及时率100%、设计使用年限≥5年；效益指标：受益人口≥520人，其中脱贫人口和监测对象≥29人，增加劳动力总收入≥1600元；满意度指标：受益对象满意度≥95%","项目建设时吸纳脱贫人口参工参运≥2人",10,29,"2025年8-12月","16万元/处","区农业农村和粮食局","区级重点帮扶村","高新区"]
[159,"乡村建设行动","排水沟","水西镇","合湖村","刘安古","新建","合湖村","老屋组","沟255m³",27,"衔接资金","产出指标：沟≥255m³、项目（工程）完成及时率100%、工程设计使用年限≥5年；效益指标：受益脱贫人口和监测对象≧92人，增加劳动力收入≥2700元；满意度指标：受益对象满意度≧95%","项目建设时吸纳脱贫人口参工参运≥1人",36,92,"2025年8-12月","27万元/处","区农业农村和粮食局","区级重点帮扶村","高新区"]
[160,"乡村建设行动","排水沟","水西镇","河坪村","彭小军","新建","河坪村","河坪组","沟300m",24,"衔接资金","产出指标：沟≥300m、项目（工程）验收合格率100%、项目（工程）完成及时率100%、工程设计使用年限≥5年；效益指标：受益脱贫人口和监测对象≧39人、增加劳动力收入≥2400元；满意度指标：受益对象满意度≧95%","项目建设时吸纳脱贫户参工参运≥1人",19,39,"2025年8-12月","24万元/处","区农业农村和粮食局","“十三五”脱贫村","高新区"]
[161,"乡村建设行动","路面硬化","水西镇","槐江村","廖有根","新建","槐江村","埠上组","路面硬化2100㎡",37,"衔接资金","产出指标：路面硬化≥2100㎡、项目（工程）验收合格率100%、项目（工程）完成及时率100%、工程设计使用年限≥5年；效益指标：受益脱贫人口和监测对象≧224人，增加劳动力收入≥3700元；满意度指标：受益对象满意度≧95%","项目建设时吸纳脱贫人口参工参运≥1人",67,224,"2025年8-12月","37万元/处","区农业农村和粮食局","普通村","高新区"]
[162,"乡村建设行动","排水沟","水西镇","槐江村","廖有根","新建","槐江村","埠上组","沟290m",20,"衔接资金","产出指标：沟≥290m、项目（工程）验收合格率100%、项目（工程）完成及时率100%、工程设计使用年限≥5年；效益指标：受益人口≥460人，其中脱贫人口和监测对象≧58人，增加劳动力收入≥2000元；满意度指标：受益对象满意度≧95%","项目建设时吸纳脱贫户参工参运≥1人",27,58,"2025年8-12月","20万元/处","区农业农村和粮食局","区级重点帮扶村","高新区"]
[163,"乡村建设行动","天意种养基地排水沟","水西镇","黄家村","黄亮","新建","黄家村","何家组","沟350m",30,"衔接资金","产出指标：沟≥350m、项目（工程）验收合格率100%、项目（工程）完成及时率100%、工程设计使用年限≥5年；效益指标：受益脱贫人口和监测对象≧74人、增加劳动力收入≥3000元；满意度指标：受益对象满意度≧95%。","项目建设时吸纳脱贫人口参工参运≥1人",32,74,"2025年8-12月","30万元/处","区农业农村和粮食局","市级重点帮扶村","高新区"]
[164,"乡村建设行动","路面硬化","水西镇","简家村","黄家保","新建","简家村","欧里组","路面硬化1260㎡",21,"衔接资金","产出指标：路面硬化≥1260㎡、项目验收合格率100%、项目完成及时率100%、设计使用年限≥5年；效益指标：受益建档立卡脱贫人口≧49人，增加劳动力总收入≥2100元；满意度指标：受益对象满意度≧95%","项目建设时吸纳脱贫人口参工参运≧1",16,49,"2025年8-12月","21万元/处","区农业农村和粮食局","普通村","高新区"]
[165,"乡村建设行动","简家村工厂化养鱼配电项目","水西镇","简家村","黄家保","新建","简家村","油珠组","250kw变压器1套及配套电缆",12,"衔接资金","产出指标：250kw变压器≥1套、项目（工程）验收合格率100%、项目（工程）完成及时率100%、工程设计使用年限≥5年；效益指标：受益脱贫人口≧9人、增加劳动力总收入≥1200元；满意度指标：受益对象满意度≧96%","促进工厂化养鱼产业发展，项目建设时吸纳脱贫人口参工参运≥1人",16,49,"2025年8-12月","12万元/处","区农业农村和粮食局","普通村","高新区"]
[166,"乡村建设行动","路面硬化","水西镇","江家村","傅小华","新建","江家村","仁村组","道路680㎡\n道路桥涵1个",20,"衔接资金","产出指标：道路≥680㎡、道路桥涵≥1个；项目验收合格率100%、项目完成及时率100%、设计使用年限≥5年；效益指标：受益脱贫人口和监测对象≥58人、增加劳动力总收入≥2000元；满意度指标：受益对象满意度≥95%","项目建设时吸纳脱贫人口参工参运≥1人",25,58,"2025年8-12月","20万元/处","区农业农村和粮食局","区级重点帮扶村","高新区"]
[167,"乡村建设行动","珊娜果业基地产业路","水西镇","彭家村","彭凯","新建","彭家村","彭家组","产业路1450㎡",23,"衔接资金","产出指标：产业路≥1450㎡、项目（工程）验收合格率100%、项目（工程）完成及时率100%、工程设计使用年限≥5年；效益指标：受益脱贫人口和监测对象≧35人，增加劳动力收入≥2340元；满意度指标：受益对象满意度≧95%","促进果业发展，项目建设时吸纳脱贫人口参工参运≥1人",16,35,"2025年8-12月","23万元/处","区农业农村和粮食局","区级重点帮扶村","高新区"]
[168,"乡村建设行动","道路硬化","水西镇","桥口村","周良","新建","桥口村","棱上组","道路硬化1375㎡",25,"衔接资金","产出指标：道路硬化≥1375㎡、项目（工程）验收合格率100%、项目（工程）完成及时率100%、工程设计使用年限≥5年；效益指标：受益脱贫人口和监测对象≧50人、增加劳动力收入≥2550元；满意度指标：受益对象满意度≧95%","项目建设时吸纳脱贫人口参工参运≥1人",25,50,"2025年8-12月","25万元/处","区农业农村和粮食局","普通村","高新区"]
[169,"产业发展","沙陂村工厂化养鱼产业项目","水西镇","沙陂村","廖春平","新建","河坪村","丰都头组","新增液态养殖罐1套",45,"衔接资金","产出指标：液态养殖罐≥1套、产业带动增加脱贫人口总收入≧100元，效益指标：受益建档立卡脱贫人口数≧46人、增加劳动力收入≥4800元；满意度指标：受益建档立卡脱贫户满意度≧95%、农业经营主体满意度≧95%","发展工厂化养鱼产业，带动产销，促进就业，项目建设时吸纳脱贫户参工参运≥1人",17,46,"2025年8-12月","据实补助","区农业农村和粮食局","“十四五”省级重点帮扶村","高新区"]
[170,"乡村建设行动","排水沟","水西镇","水西村","张国华","新建","水西村","桥头组","沟840m",15,"衔接资金","产出指标：沟≥840m；项目验收合格率100%、项目完成及时率100%、设计使用年限≥5年；效益指标：受益脱贫人口和监测对象≥9人、增加劳动力总收入≥1500元；满意度指标：受益对象满意度≥95%","项目建设时吸纳脱贫人口参工参运≥1人",4,9,"2025年8-12月","15万元/处","区农业农村和粮食局","普通村","高新区"]
[171,"乡村建设行动","路面硬化","水西镇","五星村","肖见军","新建","五星村","官田组","路面硬化320㎡",13,"衔接资金","产出指标：路面硬化≥320㎡、项目（工程）验收合格率100%、项目（工程）完成及时率100%、工程设计使用年限≥5年；效益指标：受益脱贫人口和监测对象≧9人、增加劳动力收入≥1300元；满意度指标：受益对象满意度≧95%","方便出行，项目建设时吸纳脱贫人口参工参运≥1人",3,9,"2025年8-12月","13万元/处","区农业农村和粮食局","普通村","高新区"]
[172,"乡村建设行动","江洋葡萄产业基地配套设施项目","水西镇","五星村","肖见军","新建","五星村","官田组","沟640m\n透水砖460㎡",22,"衔接资金","产出指标：沟≥640m、透水砖≥460㎡、项目（工程）验收合格率100%、项目（工程）完成及时率100%、工程设计使用年限≥5年；效益指标：受益脱贫人口和监测对象≧1193人，增加劳动力收入≥2200元；满意度指标：受益对象满意度≧95%","项目建设时吸纳脱贫人口参工参运≥1人",3,9,"2025年8-12月","22万元/处","区农业农村和粮食局","普通村","高新区"]
[173,"乡村建设行动","排水沟","水西镇","五星村","肖见军","新建","五星村","梅水组","沟330m",15,"衔接资金","产出指标：沟≥330m、项目（工程）验收合格率100%、项目（工程）完成及时率100%、工程设计使用年限≥5年；效益指标：受益脱贫人口和监测对象≧9人、增加劳动力收入≥1500元；满意度指标：受益对象满意度≧95%","项目建设时吸纳脱贫户参工参运≥1人",3,9,"2025年8-12月","15万元/处","区农业农村和粮食局","区级重点帮扶村","高新区"]
[174,"乡村建设行动","村庄整治","水西镇","下垱村","郭伟昌","新建","下垱村","龙湖组","路面硬化1900㎡\n沟107m",20,"衔接资金","产出指标：路面硬化≥1900㎡、沟≥107m、项目验收合格率100%、项目完成及时率100%、设计使用年限≥20年；效益指标：受益脱贫人口和监测对象≥28人，增加劳动力总收入≥2000元；满意度指标：受益对象满意度≥95%","项目建设时吸纳脱贫人口参工参运≥1人",10,28,"2025年8-12月","20万元/处","区农业农村和粮食局","区级重点帮扶村","高新区"]
[175,"乡村建设行动","排水沟","水西镇","珍田村","曹永平","新建","珍田村","横江组","沟280m",12,"衔接资金","产出指标：沟≥280m、项目（工程）验收合格率100%、项目（工程）完成及时率100%、工程设计使用年限≥10年；效益指标：受益脱贫人口和监测对象≥94人、增加劳动力收入≥1200元；满意度指标：受益对象满意度≧95%","项目建设时吸纳脱贫户参工参运≥1人",33,94,"2025年1-12月","12万元/处","区农业农村和粮食局","区级重点帮扶村","高新区"]
[176,"乡村建设行动","路面硬化","水西镇","珍田村","曹永平","新建","珍田村","塘下组","道路硬化596㎡",13,"衔接资金","产出指标：道路硬化≥596㎡、项目验收合格率100%、项目完成及时率100%、设计使用年限≥10年；效益指标：受益脱贫人口和监测对象≥94人、增加劳动力总收入≥1300元；满意度指标：受益对象满意度≥95%","方便出行，项目建设时吸纳脱贫人口参工参运≥1人",33,94,"2025年8-12月","13万元/处","区农业农村和粮食局","区级重点帮扶村","高新区"]
[177,"乡村建设行动","梦羚黑山羊养殖基地产业路","水西镇","珍田村","曹永平","新建","珍田村","珍田组","道路硬化1390㎡",30,"衔接资金","产出指标：道路硬化≥1390㎡、项目（工程）验收合格率100%、项目（工程）完成及时率100%、工程设计使用年限≥5年；效益指标：受益脱贫人口和监测对象≧92人、增加劳动力收入≥3000元；满意度指标：受益对象满意度≧95%","项目建设时吸纳脱贫人口参工参运≥1人",32,92,"2025年8-12月","30万元/处","区农业农村和粮食局","普通村","高新区"]
[178,"乡村建设行动","路灯","水西镇",null,"卢四敏","新建","17个村委","17个村委","太阳能路灯780盏（加山70盏、丁下40盏、汉元50盏、合湖60盏、河坪30盏、江边40盏、施家60盏、水西40盏、下垱50盏、樟村30盏、珍田60盏、彭家40盏、停孜40盏、张家30盏、桐林70盏、槐江40盏、苍坑30盏）",94,"衔接资金","产出指标：太阳能路灯≥780盏、项目验收合格率100%、项目完成及时率100%、设计使用年限≥5年；效益指标：受益脱贫人口和监测对象≥1193人、增加劳动力总收入≥9400元；满意度指标：受益对象满意度≥95%","项目建设时吸纳脱贫人口参工参运≥1人",491,1193,"2025年8-12月","94万元/处","区农业农村和粮食局",null,"高新区"]
[179,"乡村建设行动","乡村振兴示范项目农村生活污水综合治理项目-水西印象老街","水西镇",null,"艾弘任","新建","水西村","龙上组","新建1个氧化池",13,"衔接资金","产出指标：氧化池≥1个、项目（工程）完成及时率100%、工程设计使用年限≥5年；效益指标：受益脱贫人口和监测对象≧9人、增加劳动力收入≥1300元；满意度指标：受益对象满意度≧95%","解决生活污水排水问题，提升村庄环境，项目建设时吸纳脱贫人口参工参运≥1人",4,9,"2025年8-12月","13万元/处","区农业农村和粮食局","普通村","高新区"]
[180,"乡村建设行动","乡村振兴示范项目农村生活污水综合治理项目-潭隅","水西镇",null,"艾弘任","新建","潭隅村","潭隅组","地面硬化200m2\n氧化池19m³",21,"衔接资金","产出指标：地面硬化≥200㎡、氧化池≥195m³、项目（工程）验收合格率100%、项目（工程）完成及时率100%、工程设计使用年限≥5年；效益指标：受益脱贫人口和监测对象≧44人、增加劳动力收入≥2100元；满意度指标：受益对象满意度≧95%","解决生活污水排水问题，提升村庄环境，项目建设时吸纳脱贫人口参工参运≥1人",15,44,"2025年8-12月","21万元/处","区农业农村和粮食局","区级重点帮扶村","高新区"]
[null,null,"合计",{"$nulls":7},{"$f":"SUM(K4:K183)","v":2709.65}]